## Project Proposal
WEBSITE DEVELOPMENT PROPOSAL
CLIENT NAME: | Manuj Mittal
TECH STACK: | HTML/JS, Supabase, Render, Stripe/PayPal API
PHASE 1: INITIAL DEVELOPMENT & DEPLOYMENT
Component | Description | Timeline | Price (USD)
Interactive Frontend | Hero section, CSS animations, and mobile-responsive layout. | 7 Days | 200
Supabase Backend | Database setup for dynamic book data and chronicles. | 4 Days | 100
Payment Integration | Secure Checkout gateway (Stripe/PayPal) for direct book sales. | 5 Days | 150
Launch & Analytics | Render deployment, SSL security, and SEO setup. | 2 Days | 50
TOTAL ONE-TIME DEVELOPMENT FEE |  |  | 500
PHASE 2: MONTHLY MAINTENANCE & SUPPORT
Hosting & Database | Managed Render/Supabase cloud services. | Monthly | 25
Payment Security | Monitoring transaction logs and gateway health. | Monthly | 15
Content Updates | Adding new books or posts (1hr included). | Monthly | 10
TOTAL MONTHLY RETAINER |  |  | 50
TERMS & CONDITIONS
1. Advance Payment: | A 50% advance payment ($250) is required to commence development.
2. Costing Adjustments: | Final costing is subject to change based on additional feature requests or changes in project scope.